## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)
%	Phase	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed

5.00%	Phase 1: / Programming	0.4%	$563	0.5%	$675	0.5%	$788
10.00%	Phase 2: / Schematic Design	0.8%	$1,125	0.9%	$1,350	1.1%	$1,575
25.00%	Phase 3: / Design Development	1.9%	$2,813	2.3%	$3,375	2.6%	$3,938
35.00%	Phase 4: / Construction Documents	2.6%	$3,938	3.2%	$4,725	3.7%	$5,513
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$563	0.5%	$675	0.5%	$788
20.00%	Phase 6: / Construction Administration	1.5%	$2,250	1.8%	$2,700	2.1%	$3,150

100.00%	All Phases	7.5%	$11,250	9.0%	$13,500	10.5%	$15,750
Assuming a Construction Cost =							$150,000

## Hour Breakdown
Square Footage - Existing	1,700 SF
Dollar per Square Footage	88 $/SF
Total Estimated Construction Costs	$149,600.00
Architecture Fees - Percentage of Construction	8.5%
Architecture Fees	$12,716.00

Average ($/Hr) Billing Rate	$80.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people
Phase 1 - Programming	5.00%	$635.80	$635.80	8 hrs	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks
Phase 2 - Schematic	10.00%	$1,271.60	$1,907.40	16 hrs	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks
Phase 3 - Design Development	25.00%	$3,179.00	$5,086.40	40 hrs	2.0 wks	1.3 wks	1.0 wks	0.7 wks	0.5 wks
Phase 4 - Construction Documents	35.00%	$4,450.60	$9,537.00	56 hrs	2.8 wks	1.9 wks	1.4 wks	0.9 wks	0.7 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$635.80	$10,172.80	8 hrs	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	$2,543.20	$12,716.00	32 hrs	1.6 wks	1.1 wks	0.8 wks	0.5 wks	0.4 wks
	100.00%	$12,716.00	$12,716.00	159 hrs	7.9 wks	5.3 wks	4.0 wks	2.6 wks	2.0 wks